## project
Project Timeline
Project Delieverables
ACTIVITY | PLAN START | PLAN DURATION | PLAN END | 2015-09-03 | 2015-09-10 | 2015-09-17 | 2015-09-24 | 2015-10-01 | 2015-10-08 | 2015-10-15 | 2015-10-22 | 2015-10-29 | 2015-11-05 | 2015-11-12 | 2015-11-19 | 2015-11-26 | 2015-12-03 | 2015-12-10 | 2015-12-17 | 2015-12-24 | 2015-12-31 | 2016-01-07 | 2016-01-14 | 2016-01-21 | 2016-01-28 | 2016-02-04 | 2016-02-11 | 2016-02-18 | 2016-02-25 | 2016-03-03 | 2016-03-10 | 2016-03-17 | 2016-03-24 | 2016-03-31 | 2016-04-07 | 2016-04-14
Project Proposal (Draft) | 2015-09-10 | 8 | 2015-09-18
Progress Report | 2015-11-23 | 15 | 2015-12-08
Oral Presentation | 2016-01-04 | 14 | 2016-01-18
Final Report (Draft) | 2016-02-22 | 21 | 2016-03-14
Poster Fair | 2016-03-04 | 14 | 2016-03-18
Final Report | 2016-03-19 | 20 | 2016-04-08
3D Print Hand/Arm | 2015-09-03 | 22 | 2015-09-25
Hand Assembly | 2015-09-11 | 14 | 2015-09-25
Forearm Assembly | 2015-09-25 | 7 | 2015-10-02
Test Hand/Forearm Range of Motion | 2015-10-02 | 7 | 2015-10-09
[Milestone 1 - Hardware Complete] |  | 2015-10-09
Hand Control using Microcontroller | 2015-09-24 | 22 | 2015-10-16
Interface Leap Motion with Microcontroller | 2015-10-01 | 43 | 2015-11-13
Test Wired control from Leap Motion to Hand | 2015-11-13 | 14 | 2015-11-27
[Milestone 2 - Interface Established] |  | 2015-11-27
Remote Control Over Internet | 2016-01-04 | 31 | 2016-02-04
Test Latency of Remote Control over IP | 2016-01-26 | 17 | 2016-02-12
Fingertip Sensors for Closed Loop System | 2016-01-04 | 31 | 2016-02-04
Test Arm Movement and Closed Loop System (Pick up Egg test) | 2016-02-04 | 8 | 2016-02-12
[Milestone 3 - Remote Control] |  | 2016-02-12
Record Motion Feature | 2016-02-01 | 17 | 2016-02-18
Test Entire Integrated System | 2016-02-13 | 16 | 2016-02-29
[Milestone 4 - Verify Entire System] |  | 2016-02-29